SunoSathi — Phase 2 Plan

_Drafted 30 Aug 2026 · Owner: Tejas · Builder: Claude_

Where Phase 1 ended

Shipped and live: captioned calls on the user's own number (Hindi / Gujarati /

English / Hinglish, auto-detected), reply by voice / type-to-speak / picture

board, multi-tenant routing, self-registration with admin approval, Android

app in Play closed testing, iOS app in TestFlight, PWA, background ringing on

Android, noise gate, per-call quality scores, cost accounting, night-watch

sentinel, brand + website + guide + privacy policy.

Phase 2 theme

Launch, reliability, and reach. Phase 1 proved the product works. Phase 2

gets it into strangers' hands (store launches), makes sure it never misses a

call (iOS ringing, notifications), and removes every manual step between "I

signed up" and "my calls are captioned."

Workstreams

P0 — Launch blockers (weeks 1–3)

1. Play Store production release

•	
      Run the 14-day closed test with 12+ testers (in progress).

•	
      Apply for production access, fix anything Google raises.

•	
      Production listing polish: final screenshots from v0.26 UI, localized

•	
      listing (Hindi).

•	
      _Effort: mostly waiting + 1 day of fixes._

2. App Store public release

•	
      TestFlight external group + public link (one-time Beta review).

•	
      App Store listing: screenshots (6.7" + 5.5"), description, keywords,

•	
      accessibility declarations. App Review notes with the demo login.

•	
      Expect one round of App Review questions (mic + calling app); answers

•	
      largely exist from the Play data-safety work.

•	
      _Effort: 1–2 days + review wait._

3. Onboarding automation — approve → notify → forward

•	
      On approval, auto-send the setup message (forwarding code, login link)

•	
      via WhatsApp deep link the admin taps, or fully automatic via email.

•	
      Requires the email provider below; WhatsApp Business API is out of scope

•	
      (cost/verification) — manual WhatsApp send stays as the personal touch.

•	
      In-app onboarding checklist after first login: ① account approved

•	
      ② dial forwarding code ③ take a test call (button stages a sentinel-style
self-call so the user sees captions instantly without a second phone).

•	
      _Effort: 2–3 days. The self-test call is the single highest-value

•	
      onboarding feature — it turns "did it work?" into a 30-second demo._

4. Email service + OTP + password reset

•	
      Wire Resend/Brevo free tier (needs account + API key from Tejas).

•	
      Signup email OTP (6-digit), password reset flow ("forgot password" is

•	
      currently a WhatsApp-to-Tejas event), approval notification email.

•	
      Change-password UI in Settings; rotate the flagged credentials.

•	
      _Effort: 2 days._

P1 — Never miss a call (weeks 3–6)

5. iOS background ringing (CallKit + VoIP push)

•	
      The big one. Today iOS rings only with the app open.

•	
      Server: APNs VoIP push (PushKit) on incoming call → iOS wakes the app →

•	
      CallKit native ring screen → accept opens SunoSathi captions.

•	
      Needs: APNs key from the Apple developer account, push token registry

•	
      per user/device, native module work in the Expo dev-client build.

•	
      Deliverable: iPhone rings like a real phone call even when app is closed.

•	
      _Effort: 1–2 weeks including device testing. Highest engineering risk in

•	
      Phase 2 — schedule early, ship behind a per-user flag._

6. Android ring reliability hardening

•	
      Auto-restart the ring service after device reboot (BOOT_COMPLETED exists,

•	
      verify end-to-end), Doze-mode testing, battery-optimization exemption
prompt with a plain-language explanation screen.

•	
      Missed-call push summary: if a call rings 30s unanswered → notification

•	
      "You missed a call from X" (currently only visible in history).

•	
      _Effort: 3–4 days._

7. Cost optimization rung 1 (from the roadmap ladder)

•	
      Silence gating: stream caller audio to STT only when loud (loudness data

•	
      already computed). Cuts billed STT minutes 30–50%.

•	
      Smart quality re-scoring: batch re-transcribe only every 5th call plus

•	
      any call that looks broken, instead of every call.

•	
      Target: inbound all-in cost from ~₹1.5/min toward ~₹0.8/min.

•	
      _Effort: 2–3 days including a week of A/B monitoring via the sentinel._

P2 — Delight and reach (weeks 6–10)

8. Sound alerts (original phase-3 idea, promoted)

•	
      Doorbell / alarm / horn / baby crying detected on-device (YAMNet in the

•	
      browser/WebView) → vibration + full-screen flash + notification.

•	
      Works outside calls — makes SunoSathi useful all day, not only during

•	
      calls. Strong differentiator, fully on-device (no cost per minute).

•	
      _Effort: 1 week including tuning against Indian household sounds._

9. Translation bridge

•	
      Caller speaks Hindi → captions in English (or vice versa), per-user

•	
      preference. Sarvam translate API slots into the existing caption path.

•	
      _Effort: 2–3 days behind a Settings toggle._

10. Language & UI reach

•	
      Marathi / Tamil / Telugu / Bengali caption support (saaras auto-detect

•	
      already emits these — validate quality, extend script normalization).

•	
      App UI strings in Hindi and Gujarati (currently English-first with

•	
      bilingual accents).

•	
      _Effort: 3–4 days._

11. Sign-language discovery track (research, not build)

•	
      Interview 5 sign-first users (ISL) from the pilot; test whether captions

•	
      + picture board suffice or an ISL avatar layer is needed.

•	
      Output: a one-page go/no-go for an ISL interpreter feature in Phase 3.

•	
      _Effort: ongoing alongside pilot support._

Standing items (whole phase)

•	
      Key rotation (Sarvam, Vobiz, admin key, personal password) — do during

•	
      the email-service work when password reset ships.

•	
      Sentinel expansion: nightly check should also exercise type-to-speak and

•	
      the new push path once built.

•	
      Weekly cost + quality brief via Telegram (extend existing morning brief).

•	
      Google Search Console + sitemap (10-minute task, still pending).

Sequence at a glance

Weeks

Focus

1–3

Store launches, onboarding automation, email/OTP

3–6

iOS CallKit ringing, Android hardening, cost rung 1

6–10

Sound alerts, translation, languages, ISL discovery

Dependencies: everything in P0 is independent and can start now. CallKit

(5) needs an APNs key from the Apple account (Tejas, 5 minutes). Email

work (3, 4) needs a Resend/Brevo account (Tejas, 5 minutes).

Success metrics (end of Phase 2)

•	
      Both stores: public listings live, installable by anyone.

•	
      ≥ 25 approved real users; ≥ 10 weekly-active.

•	
      Missed-call rate on active users < 5% (measured via monitor).

•	
      iOS users receive calls with the app closed (CallKit live).

•	
      Inbound cost ≤ ₹0.9/min all-in.

•	
      Zero manual steps from signup to first captioned call except the

•	
      admin-approval tap.

Explicitly NOT in Phase 2

•	
      Android default-dialer "Lite mode" (parked — see ROADMAP.md).

•	
      WhatsApp Business API automation (cost/verification overhead).

•	
      Self-hosted telephony / STT (roadmap rung 3 — only at 1000s of users).

•	
      ISL avatar interpreter build (Phase 3 pending discovery outcome).